## Project Flowchart
PROJECT FLOWCHART
|  | Year 1 (June 2022-May 2023) |  |  |  | Year 2 (June 2023-May 2024) |  |  |  | Year3 (June 2024-May 2025) |  |  |  | Year 4 (June 2025-May 2026)
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
WP1 - Program Synthesis via Classical Provers
Task A.1 | bar: Year 1 (June 2022-May 2023) Q1 to Year 1 (June 2022-May 2023) Q3
Task A.2 | bar: Year 1 (June 2022-May 2023) Q3 to Year 2 (June 2023-May 2024) Q4
Task A.3 | bar: Year 1 (June 2022-May 2023) Q3 to Year 2 (June 2023-May 2024) Q4
Task A.4 | bar: Year 2 (June 2023-May 2024) Q1 to Year3 (June 2024-May 2025) Q2
Task A.5 | bar: Year3 (June 2024-May 2025) Q1 to Year3 (June 2024-May 2025) Q4
WP2 - A Program Synthesis System for Vampire
Task B.1 | bar: Year 1 (June 2022-May 2023) Q3 to Year3 (June 2024-May 2025) Q4
Task B.2 | bar: Year 2 (June 2023-May 2024) Q3 to Year 4 (June 2025-May 2026) Q2
Task B.3 | bar: Year3 (June 2024-May 2025) Q1 to Year 4 (June 2025-May 2026) Q2
Task B.4 | bar: Year 2 (June 2023-May 2024) Q1 to Year 4 (June 2025-May 2026) Q4
Milestones
M1 | bar: Year 2 (June 2023-May 2024) Q4
M2 | bar: Year3 (June 2024-May 2025) Q2; Year 4 (June 2025-May 2026) Q2
M3
M.4 | bar: Year 4 (June 2025-May 2026) Q4
| Short description of Tasks | Year3 (June 2024-May 2025) Q4: Ressources
| Task A.1: Designing a calculus with control structures suitable for program extraction from Vampire proofs | Year 4 (June 2025-May 2026) Q1: Work done mainly by Team A
| Task A.2: Establishing under what conditions non-constructive applications of control structures can be eliminated | Year 4 (June 2025-May 2026) Q1: Work done mainly by Team B
| Task A.3: Collecting characterizations of specifications for which constructiveness of the extracted program can be guaranteed | Year 4 (June 2025-May 2026) Q1: Work done mainly by Team C
| Task A.4: Examining transformation procedures for input specifications | Year 4 (June 2025-May 2026) Q1: Work done mainly by Team D
Task A.5: Evaluating the applicability, robustness and potential shortcomings of the developed mechanisms
Task B.1: Implementing the findings of WP1 into a software system
| Task B.2: Utilizing syntactic context for improved proof effectiveness | Year3 (June 2024-May 2025) Q2: Team A:; Year3 (June 2024-May 2025) Q3: Florian Zuleger, N.N (PhD student)
| Task B.3: Extending the system to restricted specifications, e.g. input/output pairs | Year3 (June 2024-May 2025) Q2: Team B:; Year3 (June 2024-May 2025) Q3: Florian Zuleger, Moritz Sinn
| Task B.4: Extensive testing and benchmarking | Year3 (June 2024-May 2025) Q2: Team C:; Year3 (June 2024-May 2025) Q3: Florian Zuleger, N.N (PhD student)
[11 empty] | Team D: | Florian Zuleger, N.N (PhD student)
Milestones:
M1: Extraction of constructive programs from classical proofs
M2: Classical provers for program synthesis via modified specifications
M3: Fully working implementation of theoretical findings
M4: A usable system for program synthesis built on top of the Vampire theorem prover