## Project Flowchart
PROJECT FLOWCHART
|  | Year 1 (June 2022-May 2023) |  |  |  | Year 2 (June 2023-May 2024) |  |  |  | Year3 (June 2024-May 2025) |  |  |  | Year 4 (June 2025-May 2026)
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
WP1 - Program Synthesis via Classical Provers
Task A.1 | bar: Year 1 (June 2022-May 2023) Q1 to Year 2 (June 2023-May 2024) Q2
Task A.2 | bar: Year 1 (June 2022-May 2023) Q3 to Year 2 (June 2023-May 2024) Q4
Task A.3 | bar: Year 1 (June 2022-May 2023) Q3 to Year 2 (June 2023-May 2024) Q4
Task A.4 | bar: Year 2 (June 2023-May 2024) Q1 to Year3 (June 2024-May 2025) Q2
Task A.5 | bar: Year3 (June 2024-May 2025) Q1 to Year3 (June 2024-May 2025) Q4
WP2 - A Program Synthesis System for Vampire
Task B.1 | bar: Year 1 (June 2022-May 2023) Q3 to Year3 (June 2024-May 2025) Q4
Task B.2 | bar: Year3 (June 2024-May 2025) Q1 to Year 4 (June 2025-May 2026) Q2
Task B.3 | bar: Year3 (June 2024-May 2025) Q1 to Year 4 (June 2025-May 2026) Q2
Task B.4 | bar: Year 2 (June 2023-May 2024) Q1 to Year 4 (June 2025-May 2026) Q4
Milestones
M1 | bar: Year 2 (June 2023-May 2024) Q4
M2 | bar: Year3 (June 2024-May 2025) Q2
M3 | bar: Year 4 (June 2025-May 2026) Q2
M.4 | bar: Year 4 (June 2025-May 2026) Q4
Short description of Tasks
| Task A.1: Designing a calculus with control structures suitable for program extraction from Vampire proofs | Year 4 (June 2025-May 2026) Q1: Staff:
| Task A.2: Establishing under what conditions non-constructive applications of control structures can be eliminated | Year 4 (June 2025-May 2026) Q1: Florian Zuleger (PI)
| Task A.3: Collecting characterizations of specifications for which constructiveness of the extracted program can be guaranteed | Year 4 (June 2025-May 2026) Q1: PhD1 (Alexander Pluska, 48 months)
| Task A.4: Examining transformation procedures for input specifications | Year 4 (June 2025-May 2026) Q1: PhD2 (N.N., 48 months)
| Task A.5: Evaluating the applicability, robustness and potential shortcomings of the developed mechanisms | Year 4 (June 2025-May 2026) Q1: PostDoc (N.N, 24 months, year 3-4)
Task B.1: Implementing the findings of WP1 into a software system
Task B.2: Utilizing syntactic context for improved proof search
Task B.3: Extending the system to restricted specifications, e.g. input/output pairs
Task B.4: Extensive testing and benchmarking
| Milestones: | Year3 (June 2024-May 2025) Q1: Workplan:
| M1: Extraction of constructive programs from classical proofs | Year3 (June 2024-May 2025) Q1: The PI Florian Zuleger will be involved in all tasks and lead A.5, B.1, B.4
| M2: Classical provers for program synthesis via modified specifications | Year3 (June 2024-May 2025) Q1: PhD1 will lead tasks A.1, A.2 and be involved in A.1,A.2,A.5,B.1,B.2.,B.3,B.4
| M3: Fully working implementation of theoretical findings | Year3 (June 2024-May 2025) Q1: PhD2 will lead tasks A.3, A.4 and be involved in A.1,A.3,A.4.,A.5,B.1,B.4
| M4: A usable system for program synthesis built on top of the Vampire theorem prover | Year3 (June 2024-May 2025) Q1: PostDoc will lead tasks B.2,B.3 and be involved in B.1,B.4